## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project initiation, define scope, setup development environment, initial planning and documentation. | MUST HAVE | No Dependency | Monish Khandelwal | 3- Completed
S2 | S1 | US-001 | Set up development environment (Expo React Native, Node.js, MongoDB) | MUST HAVE | Expo React-native Documentation | Monish Khandelwal | 3- Completed
S3 | S2 | US-001 | Set up the frontend UI by creating an Expo React Native app. Establish the basic app structure and implement the homepage and login page. | MUST HAVE | Figma(Creating UI) | Monish Khandelwal | 3- Completed
S4 | S2 | US-001 | Establish the basic app structure and implement the homepage and login page for patients, nurses, and admins. | SHOULD HAVE | Expo React-native Documentation | Monish Khandelwal | 3- Completed
S5 | S3 | US-001 | Set up the backend, implement the database schema using MongoDB, and create models and controllers for User, Patient, and Nurse. | MUST HAVE | Youtube and MongoDB | Monish Khandelwal | 2- In Progress
S6 | S4 | US-001 | Implement user registration (patients, nurses), Email-based authentication, test login/logout functionality. | MUST HAVE | Firebase and Youtube | Monish Khandelwal | 2- In Progress
S7 | S5 | US-001 | Implement patient request submission, nurse request handling, and request status tracking. | MUST HAVE | Python,Tensorflow | Monish Khandelwal | 2- In Progress
S8 | S6 | US-001 | Implement role-based access control, nurse approval workflow, assign permissions for Admin, Nurse, Patient. | SHOULD HAVE | VS Code | Monish Khandelwal | 2- In Progress
S9 | S7 | US-001 | Implement AI features(NLP Speech-To-Text), error handling, and validation middleware. Test the APIS and conduct unit and integration testing. | SHOULD HAVE | API | Monish Khandelwal | 2- In Progress
S10 | S8 | US-001 | Deploy to cloud or live server, perform final testing, fix bugs, provide documentation and installation guide. | MUST HAVE | No Dependency | Monish Khandelwal | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 10 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Set up the project repository, initialize the Expo React Native app, and configure Node.js for the backend. | 2025-03-03 | 2025-03-06 | ALL Members | Build | 3- Completed | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Design the basic app structure and implement the homepage layout in React Native using components like View, Text, and Button. | 2025-03-07 | 2025-03-10 | ALL Members | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Set up MongoDB, define schemas for User, Patient, Nurse models, and create controllers for CRED operations using Node.js and Express. | 2025-03-11 | 2025-03-17 | ALL Members | Others | 2- In Progress | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Integrate Firebase for user authentication and implement registration and login functionality for patients and nurses in Node.js. | 2025-03-11 | 2025-03-16 | ALL Members | Others | 2- In Progress | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | Develop the patient request feature(NLP IMPLEMENTATION) , allowing patients to create medical requests and view/update request statuses using React Native. | 2025-03-17 | 2025-03-23 | ALL Members | Coding | 2- In Progress | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | Implement an AI chat and role-based access control in the Node.js backend, ensuring appropriate access for admins, nurses, and patients. | 2025-03-17 | 23-03-025 | ALL Members | Coding | 2- In Progress | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | Develop error-handling middleware in Node.js, integrate user input validation, and test APIs. | 2025-03-18 | 2025-03-23 | ALL Members | Build | 2- In Progress | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | Test the mobile UI components for responsiveness and user-friendliness on different devices using Expo. | 2025-03-24 | 2025-03-26 | ALL Members | Coding | 1- Not Started | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-09 | Deploy the backend API on a cloud platform and set up environment variables for production. | 2025-03-25 | 2025-03-25 | ALL Members | Integration Test | 1- Not Started | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-10 | Document the app, including installation steps, user guide, and API documentation for backend services. | 2025-03-25 | 2025-03-26 | ALL Members | System Test | 1- Not Started | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 2 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 3 | Day 6 | Errors in the user authentication flow causing issues with login. | Focused sprint to address login and JWT token generation issues. Pair programming and code review sessions ensured fixes were done quickly.
Sprint 4 | Day 7 | Frontend UI components not responding as expected on mobile devices. | Additional testing on mobile screens. Held a meeting to address design inconsistencies and fixed UI responsiveness using figma.
Sprint 5 | Day 9 | Difficulty in integrating MongoDB and backend API endpoints | Organized a quick scrum meeting to align team on MongoDB setup. Worked through integration with mock data to ensure smooth communication with API
Sprint 6 | Day 12 | Delays in handling patient requests due to API bottlenecks. | Conducted performance review meeting. Optimized API endpoints to handle patient requests asynchronously, improving response time and flow.
Sprint 7 | Day 16 | Errors in deploying backend on the cloud. | Scheduled a debugging session with the team. Used logs and error reports to troubleshoot deployment issues. Successfully deployed after fixes.
Sprint 8 | Day 23 | Testing and debugging inconsistencies across devices and browsers. | Held a retrospective meeting to discuss testing processes. Implemented cross-platform testing with Expo, focusing on improving consistency and quality.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-03-03 | 2025-03-08 | ALL MEMBERS | Regularly review and update documentation. | Avoid working on multiple major features simultaneously. This was causing bottlenecks. | Continue having daily scrum meetings to discuss blockers and provide updates. | Focused on smaller, more manageable tasks and prioritized important features.
2 | Sprint 2 | 2025-03-10 | 2025-03-16 | ALL MEMBERS | Giving Importance on Frontend and Backend Part | Stop neglecting code reviews. Some bugs were found later due to this. | Continue following Agile methodology with sprints to stay organized. | Implemented regular code reviews and increased team collaboration for faster bug detection.
3 | Sprint 3 | 2025-03-17 | 2025-03-23 | ALL MEMBERS | Preparing CRED Operations | Avoid skipping testing on mobile devices before deployment. Issues appeared in the live version. | Keep writing clean, modular code to ensure future scalability. | stablished a mobile device testing routine to catch platform-specific issues earlier.
4 | sprint 4 | 2025-03-23 | 2025-03-26 | ALL MEMBERS | Participating in Module 1 discussions | Stop ignoring team input. Some feature designs were incomplete due to lack of collaboration. | Continue integrating feedback from testers and stakeholders to improve the app's functionality. | Held additional team sync-ups and brainstorming sessions to ensure everyone was aligned.